## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Scrum City House of Pizza Portal
| Organizations | Computer Science Team Project II: CS492
| Project | Pizza Restaurant Online Ordering System
| Product Owner | Michael Harvill
| Scrum Master | Rachael Hubble
| Development Team | Jackson Jarvie, Matthew Gimutao
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
1.1 | User Access and Experience | The user should be able to access the website or app through any device. | > The website is responsive and loads properly on mobile and desktop. > The landing page displays clearly. | 1 | 1 | Jackson Jarvie, Matthew Gimutao
1.2 | User Access and Experience | After accessing the site, the user should be able to select between picking up the pizza themselves or having it delivered. | > User can choose either "Pick-up" or "Delivery" from the main screen. > The UI clearly differentiates between the two options. | 6 | 2 | Jackson Jarvie, Matthew Gimutao
2.1 | Account Management | A new user should be able to create an account to store personal information for future use. | > User can register with email, phone, or social media accounts. > User can enter and save contact details (e.g., name, phone number, address). > User can store multiple payment methods. > User can see a history of past orders. | 7 | 2 | Jackson Jarvie, Matthew Gimutao
3.1 | Ordering and Cart Management | Users should be able to customize pizzas (size, toppings) or select from pre-built options. | > User can select a pizza from the menu. > User can customize the pizza (size, crust, toppings). > The item is added to the shopping cart with details like quantity and price. | 2 | 1 | Jackson Jarvie, Matthew Gimutao
3.2 | Ordering and Cart Management | Users should be able to review and modify their cart before finalizing the order. | > User can view all items in the cart. > User can modify quantities or remove items from the cart. | 8 | 2 | Jackson Jarvie, Matthew Gimutao
4.1 | Payment Process | Users should be able to enter their payment details and pay securely using a credit card. | > User is redirected to a secure payment gateway. > Credit card payment information is entered securely. > Payment confirmation is shown after successful transaction. | 3 | 1 | Jackson Jarvie, Matthew Gimutao
4.2 | Payment Process | If the user opts for pick-up, they should be able to choose whether to pay online or in person when picking up the order. | > The app provides an option to choose "Pay In Person" for pick-up orders. > User selects a payment method (online or in person) before checkout. | 9 | 2 | Jackson Jarvie, Matthew Gimutao
4.3 | Payment Process | After a successful payment, the user should automatically receive a digital receipt via email. | > The system sends an email receipt with order details, payment confirmation, and transaction ID. > Email is sent within a few minutes of successful payment. | 10 | 2 | Jackson Jarvie, Matthew Gimutao
5.1 | Store Owner Management | The store owner should be able to update the list of available items, including pizzas, toppings, drinks, and sides. | > Store owner can add, remove, or update menu items in the app's inventory. > System reflects real-time inventory changes (e.g., pizza availability). | 4 | 1 | Jackson Jarvie, Matthew Gimutao
5.2 | Store Owner Management | The store owner should be able to set and modify prices for all items on the menu. | > Store owner can set and adjust prices for each pizza, topping, side, and drink. > Prices are updated instantly in the app for customers. | 5 | 1 | Jackson Jarvie, Matthew Gimutao
5.3 | Store Owner Management | The store owner should be able to access and review past orders placed by customers. | > Store owner can filter orders by date range, customer, and order status. > The system provides a detailed order history, including items ordered, customer information, and total payments. | 11 | 2 | Jackson Jarvie, Matthew Gimutao

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | Pizza Restaurant Online Ordering System
|  | Sprint # |  | 1
|  | Start date |  | 2025-03-25
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07
|  | Sprint #1 Preliminary Meeting | Michael Harvill, Rachael Hubble | 2 | bar: 2025-03-27; 2025-03-29 to 2025-03-30
1.1 | 1 | The user should be able to access the website or app through any device. > Legal consideration: Accessibility. The application must meet any legal requirements for accessibility. | Michael Harvill, Rachael Hubble, Jackson Jarvie, Matthew Gimutao | 6 | 2025-03-28: 2; 2025-03-29: 2; 2025-03-30: 1
3.1 | 3 | Users should be able to customize pizzas or select from pre-built options. > Legal consideration: Intellectual Property. The application must use only licensed or original content. | Michael Harvill, Rachael Hubble, Jackson Jarvie, Matthew Gimutao | 4 | 2025-03-29: 1; 2025-03-30: 2; 2025-03-31: 1
|  | Sprint #1 Security Calibration | Michael Harvill, Rachael Hubble | 3 | 2025-03-31: 0.5; 2025-04-01: 0.5; 2025-04-03: 1; 2025-04-05: 1; 2025-04-06: 1
4.1 | 4 | Users should be able to enter their payment details and pay securely using a credit or debit card. > Legal consideration: Payment Security. The application must adhere to PCI DSS for secure payments. | Michael Harvill, Rachael Hubble, Jackson Jarvie, Matthew Gimutao | 6 | bar: 2025-03-29 to 2025-03-30; 2025-04-01 to 2025-04-02; 2025-04-05
5.1 | 5 | The store owner should be able to update the list of available items, including pizzas, toppings, and sides. | Jackson Jarvie, Matthew Gimutao | 4 | 2025-03-29: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 2
5.2 | 5 | The store owner should be able to set and modify prices for all menu items. | Jackson Jarvie, Matthew Gimutao | 4 | bar: 2025-03-30; 2025-04-05 to 2025-04-06
|  | Sprint #1 Product Demonstration | Michael Harvill, Rachael Hubble | 3 | 2025-04-06: 3
|  | Remaining units (actual) |  | 32 | #N/A | #N/A | 31 | 29 | 23 | 17 | 15.5 | 14 | 12 | 10 | 8 | 5 | 0 | #N/A
|  | Remaining units (ideal) |  |  | 29.7143 | 27.4286 | 25.1429 | 22.8571 | 20.5714 | 18.2857 | 16 | 13.7143 | 11.4286 | 9.1429 | 6.8571 | 4.5714 | 2.2857 | 1.0658e-14
[10 empty] | 0 | 32 | [5 empty] | 0 | 1.5
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Pizza Restaurant Online Ordering System
|  | Sprint # |  | 2
|  | Start date |  | 2025-04-08
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21
|  | Sprint #2 Preliminary Meeting | Michael Harvill, Rachael Hubble | 2 | 2025-04-08: 1; 2025-04-10: 1; 2025-04-13: 2
1.2 | 1 | After accessing the site, the user should be able to select between picking up the pizza themselves or having it delivered. | Jackson Jarvie, Matthew Gimutao | 3 | bar: 2025-04-10; 2025-04-12
2.1 | 2 | A new user should be able to create an account to store personal information for future use. > Legal consideration: Data Privacy and Security. The application must comply with relevant data privacy laws. > Security consideration: Encryption. All passwords must be stored and handled through secure hashing standards. > Ethical consideration: Transparency. The application must clearly state how user data will be used. > Ethical consideration: User Control. The application must allow users to manage and delete their data and accounts. | Michael Harvill, Rachael Hubble, Jackson Jarvie, Matthew Gimutao | 6 | 2025-04-09: 2; 2025-04-11: 1; 2025-04-12: 1
3.2 | 3 | Users should be able to review and modify their cart before finalizing the order. | Jackson Jarvie, Matthew Gimutao | 5 | 2025-04-10: 2; 2025-04-11: 1
4.2 | 4 | If the user opts for pick-up, they should be able to choose whether to pay online or in person when picking up the order. | Jackson Jarvie, Matthew Gimutao | 3 | bar: 2025-04-10
4.3 | 4 | After a successful payment, the user should automatically receive a digital receipt via email. > Ethical consideration: Exploitation. The application must allow the user to opt out from receiving promotional or targetted offers. | Michael Harvill, Rachael Hubble, Jackson Jarvie, Matthew Gimutao | 3 | bar: 2025-04-11; 2025-04-13
5.3 | 5 | The store owner should be able to access and review past orders placed by customers. | Jackson Jarvie, Matthew Gimutao | 3
|  | Sprint #2 Product Testing | Michael Harvill, Rachael Hubble | 4 | bar: 2025-04-13
|  | Sprint #2 Final Demonstration | Michael Harvill, Rachael Hubble | 3
|  | Remaining units (actual) |  | 32 | 31 | 29 | 24 | 21 | 19 | 15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 29.7143 | 27.4286 | 25.1429 | 22.8571 | 20.5714 | 18.2857 | 16 | 13.7143 | 11.4286 | 9.1429 | 6.8571 | 4.5714 | 2.2857 | 1.0658e-14
[10 empty] | 0 | 32 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0